## RACI Matrix
SIEMENS TEAMCENTER PLM IMPLEMENTATION — RACI MATRIX
Responsibility Assignment Matrix — who is Responsible, Accountable, Consulted and Informed per activity
Project: Teamcenter PLM Rollout |  |  |  |  | Version: 1.0 |  |  | Status: Draft for review |  |  |  | Date: ____ / ____ / ______
Phase | ID | Activity / Deliverable | Executive Sponsor (SP) | Project Manager (PM) | Business Process Owner (BPO) | Solution Architect (Siemens) (SA) | Siemens Consultants (SC) | IT Lead — Infra & Security (IT) | Engineering / CAD Lead (ENG) | Data Migration Lead (DM) | QA & Test Lead (QA) | Key Users (KU) | Training & Change Lead (TCM) | IT Operations / Support (OPS)
Phase 1 — Initiation & Planning | 1.1 | Define project charter & scope | A | R | C | C |  | I
| 1.2 | Establish governance & steering committee | A | R | C | C | [5 empty] | I
| 1.3 | Develop project plan, schedule & budget | A | R |  | C |  | C
| 1.4 | Provision dev / test / production environments |  | A |  | C | C | R | [5 empty] | I
Phase 2 — Requirements & Process Design | 2.1 | Current-state (as-is) process assessment |  | I | A |  | R |  | C |  |  | C
| 2.2 | Gather business & functional requirements (BRS) |  |  | A | C | R |  | C |  | I | C
| 2.3 | To-be process design workshops |  | I | A | R | C |  | C |  |  | C
| 2.4 | Requirements review & sign-off | I | R | A | C | C
Phase 3 — Solution Design | 3.1 | Solution architecture & BMIDE data model design |  | I |  | A | R | C | C
| 3.2 | Workflow design (change & release processes) |  |  | C | A | R |  | C |  |  | I
| 3.3 | Security model (groups, roles, ACLs) |  |  |  | A | R | C | [5 empty] | I
| 3.4 | Integration design (ERP, CAD, MES) |  |  |  | A | R | C | C
| 3.5 | Design review & sign-off (SDD) | I | A | C | R |  | C
Phase 4 — Configuration & Development | 4.1 | BMIDE template & data model configuration |  |  |  | A | R | I
| 4.2 | Workflow handlers & rules configuration |  |  | I | A | R
| 4.3 | Custom development (ITK / SOA, RAC extensions) |  |  |  | A | R | C
| 4.4 | Client configuration (Active Workspace / RAC) |  |  |  | A | R |  |  |  |  | I
| 4.5 | CAD integrations (NX, Solid Edge, multi-CAD) |  |  |  | A | R |  | C
| 4.6 | ERP / MES integration development |  |  |  | A | R | C |  | I
Phase 5 — Data Migration | 5.1 | Legacy data assessment & cleansing |  | I | A |  |  |  | C | R |  | C
| 5.2 | Migration mapping & transformation scripts |  |  | I | C | R |  |  | A
| 5.3 | Trial migration runs & reconciliation |  |  |  |  | R |  | C | A | C
| 5.4 | Cutover plan & final data load |  | I |  |  | R | C |  | A |  |  |  | C
Phase 6 — Testing | 6.1 | Unit & configuration testing |  |  |  | A | R |  |  |  | I
| 6.2 | System integration testing (SIT) |  |  |  |  | R | C |  | C | A
| 6.3 | User acceptance testing (UAT) |  | I | A |  | C |  |  |  | C | R | C
| 6.4 | Performance & load testing |  |  |  | A | C | R | [5 empty] | C
| 6.5 | Defect triage & resolution |  | A | I |  | R |  |  |  | C
Phase 7 — Training & Change Management | 7.1 | Training material development |  |  | C |  | C |  |  |  |  | I | A/R
| 7.2 | Admin & end-user training delivery |  |  |  |  | C |  |  |  |  | I | A/R
| 7.3 | Communication & change management plan | I | C | C | [7 empty] | A/R
| 7.4 | Support model & hypercare readiness |  | A |  |  | C | [5 empty] | C | R
Phase 8 — Go-Live & Support | 8.1 | Go / No-Go decision | A | R | C | C |  | C |  |  | C | I
| 8.2 | Production cutover & go-live | I | A |  |  | R | R |  | C |  |  |  | C
| 8.3 | Hypercare support |  | A |  |  | R |  |  |  |  | I | C | R
| 8.4 | Transition to steady-state support (AMS) |  | I |  |  | C | R | [5 empty] | A
| 8.5 | Project closure & lessons learned | A | R | C | C | [5 empty] | I
Rules: every activity has exactly one Accountable (A) and at least one Responsible (R). Edit any cell via the drop-down (R / A / C / I / A/R) — colours update automatically.

## Role Definitions
ROLE DEFINITIONS & ABBREVIATIONS
Abbr. | Role | Side | Typical responsibilities
SP | Executive Sponsor | Customer | Owns the business case, funding and final Go/No-Go decisions; chairs the steering committee.
PM | Project Manager | Joint (Customer + Siemens) | Plans, tracks and delivers the project; manages scope, schedule, budget, risks and escalations.
BPO | Business Process Owner | Customer | Owns the to-be business processes and requirements sign-off; prioritises functional scope.
SA | Solution Architect (Siemens) | Siemens | Owns the overall Teamcenter solution architecture, BMIDE data model and technical design integrity.
SC | Siemens Implementation Consultants | Siemens | Configure and customise Teamcenter: BMIDE, workflows, security model, integrations and migration tooling.
IT | IT Lead — Infrastructure & Security | Customer | Provides servers, networking, identity management, security reviews and production infrastructure.
ENG | Engineering / CAD Lead | Customer | Represents engineering: CAD data, NX/Solid Edge integrations, drawing and release practices.
DM | Data Migration Lead | Joint | Owns legacy-data strategy, cleansing, mapping, trial loads, reconciliation and final cutover load.
QA | QA & Test Lead | Customer | Owns test strategy, SIT/UAT execution, defect tracking and quality exit criteria.
KU | Key Users | Customer | Process experts per department; validate requirements, execute UAT, champion adoption.
TCM | Training & Change Mgmt Lead | Customer | Owns training materials, delivery, communications and organisational change management.
OPS | IT Operations / Support | Customer | Runs hypercare and steady-state Teamcenter operations, monitoring and incident management.

## Legend & Guide
LEGEND & HOW TO USE THIS MATRIX
Code | Meaning | Description
R | Responsible | Does the work to complete the activity. At least one R per activity; can be shared.
A | Accountable | Owns the outcome and gives final sign-off. Exactly one A per activity.
C | Consulted | Provides input before the work is done (two-way communication).
I | Informed | Kept up to date after decisions or completion (one-way communication).
A/R | Accountable & Responsible | Same small role both owns and performs the work (used sparingly).
Ground rules
1. Every activity has exactly ONE Accountable and at least one Responsible.
2. The Executive Sponsor is Accountable only for charter, Go/No-Go and closure — not delivery tasks.
3. Siemens roles (SA, SC) are Accountable for solution design and configuration quality; the customer PM is Accountable for overall delivery.
4. Keep Consulted limited to people whose input genuinely changes the outcome.
5. Review the matrix with all leads at project kick-off and re-validate at each phase gate.
6. To adapt: add/remove activities in the matrix sheet, extend the role columns, and use the drop-downs in each cell.
Phases covered
• Phase 1 — Initiation & Planning (4 activities)
• Phase 2 — Requirements & Process Design (4 activities)
• Phase 3 — Solution Design (5 activities)
• Phase 4 — Configuration & Development (6 activities)
• Phase 5 — Data Migration (4 activities)
• Phase 6 — Testing (5 activities)
• Phase 7 — Training & Change Management (4 activities)
• Phase 8 — Go-Live & Support (5 activities)