## Current tasks
Siemens CAST AI — tasks in progress (generated 2026-10-02)
# | Task | Category | Thread / ticket | Status | Next action / blocked on | Key artifacts | Last touched
1 | NGM EKS savings analysis + reply to Gerolf (helios/integ/kronos): verdict — CAST AI beneficial on all 3 clusters (~$17k/mo net conservative); P1: node-template/spot tuning ($19–36k/mo), P2: WOOP agent upgrade + AMI family, P3: unpinned AMI, interruption-prediction update, rebalancing freq; reply draft ready to send | Customer analysis | Gerolf Reinwardt email 2026-09-15; clusters ngm-helios / ngm-integ / ngm-kronos-eks (org 07aa3c29-…) | In progress — analysis DONE 2026-10-02, reply pending review/send | Review draft reply (labs/si-gsw-sep30-meeting/REPLY-anomaly-docs-gerolf.md), human sends; then offer recurring 3-column savings table (actual ¦ frozen-baseline ¦ CAST realized) + P1/P2/P3 tuning plan | .kimchi/docs/si-gsw-clo-ngm-cost-savings-analysis-2026-10.md; cluster-cost-analysis/ngm-*/ (raw JSON); scripts/savings/savings_report.py; labs/si-gsw-sep30-meeting/ | 2026-10-02
2 | Anomaly-detection documentation (CAST-side action item) | Docs commitment | Aug 19 GSW meeting notes A10 + Gerolf email item 4 | Open — verified 2026-10-02 that no public docs exist | Commit a delivery date for the anomaly-docs write-up BEFORE the rescheduled GSW meeting; interim: bell/webhook/Slack notifications docs are the closest public reference | .kimchi/docs/si-gsw-meeting-prep-2026-10-02-verification.md (§A10, §E) | 2026-10-02
3 | GSW follow-up session 2 prep — Suresh: 2.4 GB memory request / blocked DaemonSet | Session prep | Suresh session invite (Friday) | Waiting on customer answers | 5 open questions (which pod holds 2.4 GB request; which DS blocked; cluster+org id; WA mode active?; owner + change path Helm vs annotation). Clarify draft is draft-only, human sends | .kimchi/docs/siemens-castai-followup-session2-prep.md (§6 fix levers, §7 open questions) | 2026-10-02
4 | Org structure decision follow-up (per-team org vs BU consolidation) | Meeting follow-up | 'Cast AI & Siemens — Cast AI Org Structure' meeting 2026-10-02 12:00 | Recommendation delivered — record final decision | Recommendation: keep per-team model, do not restructure mid-rollout; after meeting, record decision + next steps in brain | .kimchi/docs/siemens-org-structure-options-2026-10-02.md | 2026-10-02
5 | CreateTags Case — TKT-20260817-b640 (ec2:CreateTags explicitDeny) | Support case | TKT-20260817-b640; Jira CSO-10662 / CSO-11111; account 238720913587 | BLOCKED on Siemens CSO input | Awaiting full SCP JSON for every policy on the OU path (or IAM Policy Simulator output); meanwhile onboard cluster in read-only / Workload Autoscaler mode; confirm Windows castctl has no cso tag | brain/notes/CreateTags Case.md; labs/csi-tagcheck/; .kimchi/docs/tkt-20260817-b640-createtags-scp-runbook.md | 2026-09-29
6 | PutRolePolicy 403 Case — Conceptboard autoscaling onboarding | Support case | Conceptboard (Siemens engagement) — account 951463557399, cluster siemenstest-siemenstest-1 | Reply drafted — awaiting human send; fix not yet applied | Send REPLY-to-samuel.md; then Siemens adds iam:PutRolePolicy(+Get/Delete) scoped to cast-* roles, re-run connect (idempotent); enable Node Autoscaler; console invite for samuel.frunza@…; rotate circulated connect token | brain/notes/PutRolePolicy 403 Case.md; labs/putrolepolicy-403/ | 2026-10-01
7 | MCP server / dashboard key scoping decision | Tooling decision | MCP key currently binds default empty org | Decision pending | Decide whether to swap MCP key for the enterprise key (org-allow-listed) so MCP tools see the Siemens fleet | brain/BRAIN.md (priority 2); .kimchi/docs/castai-mcp-security.md | 2026-10-01
8 | Fleet inventory upkeep for engagement reporting | Reporting | Siemens fleet | Recurring | Keep cluster-readiness-outputs/castai_cluster_inventory.xlsx current (orgs, clusters, agent health) | cluster-readiness-outputs/castai_cluster_inventory.xlsx; brain/notes/Siemens Fleet.md | 2026-09-11
9 | Commit untracked work-in-progress | Housekeeping | git working tree | Not started | Untracked: cluster-cost-analysis/ (raw NGM JSON), diagnose-castai-memory.sh + fix-castai-memory.sh, labs/si-gsw-sep30-meeting/ (august-api-numbers, savings-analysis), projects/castai-support-swarm/fixtures/thread-siemens-gsw-workshop-move.md | git status | 2026-10-02

## Recently delivered
Item | Delivered | Where
NGM savings methodology + reproducible savings_report.py | 2026-10-02 | .kimchi/docs/siemens-savings-methodology.md; scripts/savings/
GSW Sep 30 meeting data-verification brief (claim-by-claim) | 2026-10-02 | .kimchi/docs/si-gsw-meeting-prep-2026-10-02-verification.md
Org-structure options deck prep (rev 2, 30-idea pool) | 2026-10-02 | .kimchi/docs/siemens-org-structure-options-2026-10-02.md
Support swarm: plan verification + review + eval harness | 2026-09-29 | .kimchi/docs/plan-verification-support-swarm.md; review-support-swarm.md
Token-rotation E2E verification + runbooks | 2026-09-16 | .kimchi/docs/token-rotation-e2e-status.md; rotate-token-manual-commands.md
Karpenter vs CAST AI claims verification (fact-check) | 2026-09-24 | .kimchi/docs/siemens-karpenter-vs-castai-claim-check.md